Consultancy Terms of Reference: Documentation of Siyakha Results and Opportunities

Background:

John Snow Research and Training Institute Inc., through its World Education Division, seeks to engage an expert consultant to compile and document results achieved from the implementation of the Siyakha model.

Siyakha, a holistic workforce development model developed by World Education, is recommended by PEPFAR as one of the approved evidence-based models for comprehensive economic strengthening for adolescent girls and young women in DREAMS programming.  World Education developed Siyakha through over a decade of experience and experimentation to identify what works for adolescent girls and young women to be able to successfully enter the workplace or engage in entrepreneurship. This adaptable model underscores the significance of the right skills set and support system, customized to actively involved adolescent girls and young women, their families or spouses.  This approach leads to positive outcomes, even in economically constrained or informal settings.  Presently, Siyakha is being implemented by World Education, Bantwana Zimbabwe, and numerous other DREAMS implementing partners in Malawi, Mozambique, Namibia, South Africa, Zambia, and Zimbabwe. Bantwana Zimbabwe a local affiliate of World Education serves as the certified regional technical assistance provider for Siyakha, offering technical support and monitoring to all organizations implementing Siyakha within the framework of DREAMS.

Objectives of the consultancy:

The purpose of the consultancy is to generate insights about the breadth and depth of Siyakha results across all countries where Siyakha is implemented.

- Analyze and document the reach of Siyakha

- Analyze and document the performance of Siyakha on key process and outcome indicators, highlighting any noteworthy patterns or trends

- Identify key challenges and lessons learned across diverse settings

- Analyze the effectiveness of Siyakha in promoting workforce readiness for adolescent girls and young women

- Identify recommendations for improving the documentation of Siyakha results across diverse settings

The consultancy will be conducted in two phases: a desk review phase and a data collection phase.

Desk review:  The consultant will be provided with the Siyakha implementation toolkit, M&E indicator guidance, implementation reports, work plans, and data culled the Siyakha database in CommCare.  The consultant will also be provided with technical assistance reports and training reports from the Bantwana Zimbabwe technical assistance support visits, as well as documentation from a lessons learned Siyakha implementation workshop convened for Siyakha implementing partners. These materials will serve as the primary source of the data for analysis and synthesis during the desk review.  The consultant will analyze this information to present the comprehensive results of Siyakha based on key process and outcome indicators, identifying significant patterns and trends. The consultant will compile the results of the desk review into a comprehensive slide deck that will be presented to World Education.

Stakeholder consultations: The consultant will build on the results of the desk review to conduct stakeholder interviews that will include:

- Siyakha implementing partners across the various DREAMS implementing partners (which may include sampling from the following projects -  the Ana Patsogolo Activity in  Malawi implemented by JSI; The Gateway project in Malawi implemented by JPHEIGO; The Adolescents and Children HIV Incidence-Reduction Empowerment and Virus Elimination (ACHIEVE) project i Namibia implemented by PACT; the DREAMS Initiative in Namibia implemented by Project Hope; The Chengetai Wana Project in Mozambique implemented by ANDA; The Zambia Community HIV Prevention (ZCHPP) project in Zambia implemented by PACT; DREAMS in South Africa implemented by FHI360;  and the CHECKUP! project in Zambia implemented by the Centre for Infection Disease Research)

- Technical experts from Bantwana Zimbabwe and World Education,

- PEPFAR DREAMS coordinators and USAID representatives;

- Technical and Vocational Education Training (TVET) representatives,

- Representatives from the private sectors who employed or offered internships or placements to Siyakha participants;

- Care and spouses of Siyakha graduates;

- Siyakha graduates.

The stakeholder consultations will be qualitative in nature and conducted through a combination of virtual and face to face meetings.  The stakeholder interviews may include both key informant interviews and focus group discussions.  World Education and Bantwana Zimbabwe will facilitate contact information and introductions as needed. The stakeholder interviews will complement, deepen and the data compiled during the desk review phase.  By engaging directly with individuals who have firsthand experience related to Siyakha, the stakeholder interviews will provide a richer and more comprehensive understanding of the results achieved.

Deliverables:

| Deliverable | Description | Estimated Level of Effort |
| --- | --- | --- |
| Inception report | Detailed work plan and methodology, including proposed stakeholder consultation interview and focus group discussion guides | 1.5 days |
| Desk Review Slide Deck | Detailed slide deck summarizing the comprehensive results of Siyakha based on key process and outcome indicators, and identifying significant patterns and trends. | 2.5 days |
| Stakeholder Consultations | The consultant will propose a schedule of stakeholder consultations and set of interview questions and or focus group discussion guides | 6.5 days (4.5 days consultations and 2 days synthesis) |
| Draft Report | Draft comprehensive report that synthesizes the desk review and insights gained from the stakeholder consultations | 4 days |
| Final Report | Final comprehensive report that synthesizes the desk review and insights gained from the stakeholder consultations | 2 days |
| Weekly one-hour check in meetings | The consultant will meet weekly with the World Education team to review progress against the workplan and to provide feedback. | .5 days |
| Total LOE |  | 17 days |

Timeline:

The consultancy is expected to be completed between November 15 and January 30. The total number of billable days within this time frame is not to exceed 17.

Qualifications:

The consultant should possess the following qualifications and experience:

- Knowledge and expertise in economic empowerment, workforce readiness, gender equity and social inclusion, and integrated programming approaches;

- Advanced analytical and problem-solving skills

- Ability to draft and communicate high quality and concise outputs

- Proven expertise in conducting landscape analyses and assessment in economic empowerment or other related fields

- Capacity to set priorities, self-organize, plan, and deliver tasks on time;

- Strong research and analytical skills

- Excellent written and oral communication skills.

Interested candidates should submit applications to bantwana@worlded.org no later than Sunday, November 12, 2023. The application should contain:

- Cover letter describing consultant’s interest, qualifications, and experience to complete the work

- CV highlighting relevant work experience and qualifications to complete the work described in the terms of reference above

- High level work plan and methodology that outlines their proposed approach for completing this assignment.

- Three references

- Daily consultancy rate